## Goods
ACBF PROJECT PROCUREMENT PLAN - 11th SEPTMBER, 2012 | PAMI PROJECT PROCUREMENT PLAN JANUARY - DECEMBER 2019
1. | General
| Country/Organisation: |  |  | African University of Science and Technology, (AUST), Abuja, Nigeria
| Project/Programme: |  |  | Pan African Materials Institute (PAMI)
Loan No:
| Implementing Agency, Address: |  |  | African University of Science and Technology, (AUST), Abuja, Nigeria
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: |  |  | 1st January, 2019 - 31st December, 2019
G O O D S
2. | Prior Review Threshold:
Goods and Non-Consulting (see Note 1)
|  |  |  | Threshold | Prior review
| Procurement Method |  |  | for use of Method | Threshold | Comments
|  |  |  | (US$) | (US$)
| 1. ICB and LIB (Goods) |  |  | = or > 250,000 | 250,000
| 2. NCB (Goods) |  |  | > 50,000 and <250,000 | None
| 1. ICB (Works) |  |  | N/A | N/A
| 4. NCB (Works) |  |  | N/A | N/A
| 5. ICB (Non-Consultant Services) |  |  | 250,000 | 250,000
| 6. Shopping |  |  | < 50,000 | None
| 7. Direct Contracting |  |  | None | 1,000
3. | Procurement Packages with Methods and Time Schedule |  |  |  | BASIC DATA | [7 empty] | Bid Documents |  |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation
| Description of Contract | Package | Lot | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Specific Notice/ Advert | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date
| Procurement of mini battery manufacturing equipment | 1 | 1 | WB | 50000 | Direct Contracting | Post- Qualification | N/A | Post Review | 2019-04-04 | 2019-05-02 | Plan | N/A | N/A | 2019-04-04 | 2019-04-04 | 2019-05-02 | 2019-05-30 | N/A | 400,000 | 2019-06-27 | 2019-07-18 | 2019-07-25 | 2019-10-25
Actual
| Procurement of Solar and OLED PV Test Equipment as well as 60 KW Solar Farm to Supply Power to PAMI Research Laboratory |  | 2 | WB | 120000 | Request for quotation | Post- Qualification | N/A | Post Review | 2019-04-04 | 2019-05-02 | Plan | N/A | N/A | 2019-04-04 | 2019-04-04 | 2019-05-02 | 2019-05-30 | N/A | 400,000 | 2019-06-27 | 2019-07-18 | 2019-07-25 | 2019-10-25
Actual
| Procurement of Battery Deposition and Characterization Equipment along with Pressure Assisted Fabrication Equipment, Current Voltage Characterization Equipment, 40 Units of Vex Robots and 4 Units of 3D Printers, Accessories and Software | 2 | 1 | WB | 220000 | Direct Contracting | Post- Qualification | N/A | Post Review | 2019-04-04 | 2019-05-02 | Plan | N/A | N/A | 2019-04-04 | 2019-04-04 | 2019-05-02 | 2019-05-30 | N/A | 220,000 | 2019-06-27 | 2019-07-18 | 2019-07-25 | 2019-10-25
Actual
| Procurement of Laptops, 5Nr Videoconferencing Equipment, Touch Screen Computers and Projectors |  | 2 | WB | 100000 | Request for quotation | Post-Qualification | N/A | Post Review | 2019-06-04 | 2019-07-02 | Plan | N/A | N/A | 2019-06-04 | 2019-06-04 | 2019-07-02 | 2019-08-30 | N/A | 245,000 | 2019-09-06 | 2019-09-13 | 2019-09-20 | 24--Dec-18
Actual
| Subscription to NgREN Broadband Access and Accessories as well as Scopus Renewal |  | 3 | WB | 44000 | Direct Contracting | Pre Qualification | N/A | Post Review | 2019-06-04 | 2019-06-25 |  | N/A | N/A | N/A | N/A | N/A | 2019-08-15 | N/A | 44,000 | 2019-08-29 | 2019-09-05 | 2019-09-19 | 2019-10-26
| TOTAL COST |  |  |  | 534000
[14 empty] | N/A | 2019-06-06 | 2019-06-06 | 2019-07-04 | 2019-08-01
[14 empty] | N/A | 2019-06-06 | 2019-06-06 | 2019-07-04 | 2019-08-01
[14 empty] | N/A | 2019-06-06 | 2019-06-06 | 2019-07-04 | 2019-08-01
[14 empty] | N/A | 8-Jun-19 | 8-Jun-19 | 6-Jul-19 | 1-Aug-19
[14 empty] | NA | 7-Mar-19 | 7-Mar-19 | 4-Apr-19 | 2-May-19
Page 1/3

## Services
Description of Contract | Package | Lot | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Specific Notice/ Advert | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date
Professional Services (Legal, Accounting, etc) | N/A | N/A | WB | 17500 | LCS | Pre Qualification | N/A | Post Review | 2019-05-08 | 2019-06-05 | Plan | N/A | N/A | 2019-05-08 | 2019-05-08 | 2019-06-05 | 2019-07-03 | N/A | 17,500 | 2019-07-31 | 2019-08-21 | 2019-08-28 | 2019-10-03
Actual